ASAN INNOVATORS

Building Beyond Boundaries

Statement of Work

Prime Tracker — Interior / Fit-Out Module & Sale Payment Schedule

| Prepared by | Kalyan Kumar Bedugam (AK), Asan Innovators |
| --- | --- |
| Prepared for | Prime Developers — Attn: Founder / Co-Founder |
| Document | Statement of Work (SOW) |
| Version | v1.0 |
| Date | 30 May 2026 |
| Engagement | Prime Tracker platform extension — two coupled feature modules |
| Project Start Date | ____________________ (to be confirmed on signature) |

# Contents

# 1. Project Overview

Client: Prime Developers (the “Client”).

Provider: Asan Innovators (the “Provider”).

Prime Tracker is the Client’s internal real-estate development management platform. This engagement extends the existing platform with two closely related capabilities that are delivered together as a single release train.

## 1.1 Problem Statement

Prime builds the shell of a unit through its existing construction workflow, and for many units then performs a separate interior fit-out. Today the platform has no representation of the fit-out engagement, and a sale records only a single total price with no schedule of when the buyer’s money is due. As a result, interior progress is tracked outside the system and the cash-flow forecast cannot show real money-in dates.

## 1.2 Solution Summary

- Interior / Fit-Out Module — a structured, seven-phase fit-out workflow per unit, with an isolated interior (TI) budget, sub-contractor invoice tracking, a snagging / punch list, and document-gated handover.

- Sale Payment Schedule — a milestone-linked installment schedule on each sale that drives overdue-payment alerts and feeds the platform’s cash-flow forecast.

The two features are coupled: the client-facing interior charge is one of the sale installments, triggered on interior handover. They are therefore scoped, built, and delivered as one engagement.

# 2. Scope of Work

## 2.1 In Scope

Feature A — Interior / Fit-Out Module:

- Interior project record anchored to a unit (or building), supporting more than one fit-out over a unit’s lifetime.

- Seven-phase workflow: Design → Client Approval → City Approval → Procurement → Execution → Snagging → Handover, with a controlled state machine.

- Soft sequencing rule: Procurement and Execution are blocked until the unit’s shell is complete; design and approval phases may begin earlier.

- Document gates: city-approval document required before Execution; handover certificate required before Handover.

- Per-square-foot contract pricing, with support for fixed and cost-plus as alternatives.

- Isolated interior (TI) budget and actuals, reported as a top-level cost category separate from construction.

- Sub-contractor invoice tracking per interior project, linked to existing vendor records.

- Scope / bill-of-quantities line items, including two to three reusable fit-out package templates.

- Snagging / punch list with status, assignee, and photo evidence.

- Cross-project Interior Portfolio view (phase, budget vs. actual, days to handover) and a per-unit Interior tab.

Feature B — Sale Payment Schedule:

- Installment schedule on each sale, supporting fixed-date and construction-milestone triggers.

- Automatic due-date stamping when a linked milestone completes.

- Partial-payment handling and percentage-of-price or fixed-amount installments.

- Schedule templates for the Client’s standard installment structures.

- Overdue and upcoming-payment alerts via the existing in-app and email notification system.

- Integration of scheduled installments into the platform’s cash-flow forecast and a Finance “upcoming receivables” view.

Cross-cutting (both features):

- Role-based access control for the new capabilities, consistent with the existing permission model.

- Audit logging of all new write operations, using the platform’s existing audit mechanism.

- Automated tests for the new business logic, and one combined database migration.

- Knowledge-transfer walkthrough of the delivered features.

## 2.2 Out of Scope

- Broker / referral commission tracking (separate future engagement).

- Unit-grouping / combining adjacent units into one legal unit.

- Daily construction photo logs.

- BuilderTrend and Bill.com integrations (e.g., automated purchase-order transfer).

- WhatsApp notification channel (email and in-app only for this engagement).

- Sale cancellation / refund-and-penalty workflow.

- Multi-currency support (USD only).

- Data migration of historical interior or payment records (can be quoted separately if required).

# 3. Technical Approach

Both features are implemented within the existing Prime Tracker architecture and follow established platform conventions, so they integrate cleanly with current modules.

| Layer | Technology |
| --- | --- |
| Backend | NestJS modular monolith with Prisma v5 and PostgreSQL |
| Frontend | React 18 + Vite, HeroUI component library, TanStack Query |
| Eventing | Existing in-process domain event bus (no new module coupling) |
| Scheduling | Existing daily scheduled-jobs mechanism for overdue checks |
| Files | Existing managed file storage for photos and certificates |

Architectural commitments: the interior module is delivered as a self-contained module mirroring the existing draw-workflow module; interior costs reuse the existing budget and actuals tables but are reported as a distinct category; the client-facing interior price is recorded on the sale as an installment; and all cross-feature behaviour is wired through the existing event bus. The change set is additive — no existing data structures are altered destructively.

# 4. Timeline & Milestones

Timeline is expressed in weeks relative to the confirmed Project Start Date. Durations are indicative and will be confirmed at kickoff. Delivery is incremental: each milestone produces working, demonstrable functionality.

| Milestone | Deliverable | Target (from start) |
| --- | --- | --- |
| M0 — Discovery & Sign-off | Resolve open requirements (Section 6), confirm payment-schedule templates and interior packages, finalise data model. | Week 1 |
| M1 — Foundation | Combined database migration; interior project records with the seven-phase workflow and sequencing gate; per-unit Interior tab; sale installment schedule with milestone linkage. | Weeks 2–4 |
| M2 — Financials | Isolated interior budget and actuals with top-level TI reporting; sub-contractor invoice tracking; payment logging with partial payments; cash-flow inflow integration. | Weeks 5–6 |
| M3 — Scope & Automation | Bill-of-quantities and 2–3 package templates; milestone-completion automation; overdue and upcoming-payment alerts; Finance receivables view. | Weeks 7–8 |
| M4 — Snagging, Handover & Hardening | Snagging / punch list; document gates and handover certificate; Interior Portfolio view; automated tests, fixes, and knowledge transfer. | Weeks 9–10 |

Indicative total duration: approximately 10 weeks from the confirmed start date, assuming timely Client input at Milestone M0 and during review cycles.

# 5. Assumptions & Dependencies

- The engagement builds on the current Prime Tracker codebase and its existing modules (construction, sales, milestones, budgets, vendors, documents, notifications, cash-flow); these remain available and stable for the duration.

- The Client provides timely access to a working development/staging environment and any required credentials.

- The Client nominates a single point of contact empowered to answer requirements questions and approve milestones.

- Interior fit-outs are managed by the existing Project Manager role; no new organizational role is introduced.

- Email and in-app notifications use the Client’s existing configured channels.

- The following items are confirmed during Discovery (M0) and are assumed resolvable within that milestone without changing overall scope:

  - Whether the existing sale deposit becomes the first scheduled installment.

  - The Client’s one or two standard payment-schedule templates.

  - Which roles may record payments, and the approver of record for City Approval.

  - The two to three standard interior package definitions.

  - Whether interior contract values require field-level encryption.

- Reviews are completed within two business days of delivery for each milestone to keep the timeline on track.

# 6. Discovery Items to Confirm at Kickoff

The following design questions are intentionally resolved during Milestone M0 so that build work proceeds against confirmed decisions. They do not block signature.

- Deposit handling — fold the existing sale deposit into the installment schedule, or keep it separate.

- Standard payment-schedule template(s) used by Prime.

- Permission to record payments — Finance/Accounting only, or also Sales.

- City Approval approver of record within the system.

- Interior package definitions (2–3 standard packages), or model-now / populate-later.

- Whether interior contract values should be encrypted like loan financial fields.

# 7. Terms & Conditions

## 7.1 Intellectual Property

All source code and deliverables produced under this SOW are work-for-hire and become the property of the Client upon delivery, save for any pre-existing Provider tools, libraries, or generic components, which the Provider retains and licenses to the Client for use within Prime Tracker.

## 7.2 Revisions

Each milestone includes up to two rounds of review and revision against the agreed scope. Changes that expand scope beyond this SOW are handled through a written change request.

## 7.3 Change Management

Any change to scope, deliverables, or timeline is documented in a change request and agreed in writing by both parties before work proceeds.

## 7.4 Communication Cadence

A short weekly progress update and a demonstration at each milestone. The Client’s nominated point of contact is responsible for consolidating Client-side feedback.

## 7.5 Commercial Terms

Commercial terms — fees and payment schedule — are addressed in a separate commercial annex and are intentionally not included in this Statement of Work.

## 7.6 Termination

Either party may terminate this engagement with written notice. On termination, the Client receives all completed and in-progress deliverables, and settlement is made for work performed up to the termination date per the separate commercial annex.

# 8. Acceptance & Sign-off

By signing below, both parties agree to the scope, approach, timeline, and terms set out in this Statement of Work.

| For Asan Innovators | For Prime Developers |
| --- | --- |
| Name: Kalyan Kumar Bedugam (AK) | Name: ________________________ |
| Title: Principal / Engagement Lead | Title: Founder / Co-Founder |
| Signature: ________________________ | Signature: ________________________ |
| Date: ________________________ | Date: ________________________ |